## Sheet1
Item # | Description | Mandatory, Desired, Optional | Response | Vendor Comment/Solution - Response Codes “F” and “P” require a written response describing how and when the specification will be met.
Yes, No, Future, Partial
A. PROJECT INITIATION
A-1 | Meet with City staff on project intent and planning process (prefer in person meetings) | M
A-2 | Review and analyze existing site conditions | M
A-3 | Review and evaluate options for site elements | M
A-4 | Review current Parks, Recreation and Other Recreation Facilities Master Plan | M
A-5 | Site Analysis | M
A-6 | Park Site Tour with City staff | M
B. ENVIRONMENTAL REVIEW/STUDY
B-1 | Prepare the appropriate CEQA analysis and document | M
B-2 | Prepare Final CEQA document | M
B-3 | Prepare any necessary findings and resolution for certification of environmental document | M
B-4 | Prepare environmental documents for public noticing and filing | M
C. CONCEPTUAL DESIGN IDEAS AND REVISIONS
C-1 | Refine conceptual design for the site elements | M
C-2 | Prepare dimensioned site plans, elevations and colored renderings to be used for final approvals and as a basis for preparation of construction documents | M
D. PUBLIC MEETINGS AND PRESENTATIONS
D-1 | Attend a minimum of four (4) meetings with staff to review and discuss designs throughout project duration | M
D-2 | Attend and facilitate two community meetings to discuss design proposal and receive public input | M
D-3 | Prepare and present a PowerPoint presentation at a Parks, Recreation and Culture Commission meeting | M
D-4 | Prepare and present a PowerPoint presentation to two City Council meetings | M
D-5 | Provide one follow-up presentation to one or more of the above, if required | M
D-6 | Create outreach plan with ideas for outreach (online workshop tools, real time graphics, etc.) | D